## Executive Summary
Evidence and Assumption Register
Separates verified production facts from hypotheses and owner decisions.
Generated | 2026-08-14 17:31 ET
Data classification | Operational metadata only - no secrets, private BCC, or live customer PII

## Evidence Register
Evidence Register
Do not convert assumptions into claims.
ID | Statement | Classification | Status | Source | Verified date | Owner | Next review | Notes
E-001 | AskMagicMike.com serves the canonical app | Evidence | VERIFIED | Vercel deployment dpl_3io4gCpEE3yeDgTSGSGV1D8p5RMe | 2026-08-14 | System owner | After next deploy | HTTP 200; apex 308
E-002 | Form 3 creates one canonical lead and one internal alert | Evidence | VERIFIED | docs/FORM3_PRODUCTION_RECONCILIATION.md | 2026-08-14 | System owner | Daily | Replay idempotent
E-003 | Neon contains six production test leads and zero live prospects at audit | Evidence | POINT-IN-TIME | Neon production aggregate | 2026-08-14 | System owner | Daily | Does not include WordPress shadow entry 1550
E-004 | Web Push has zero active devices | Evidence | VERIFIED | Neon staff_push_subscriptions aggregate | 2026-08-14 | System owner | After enrollment | Email remains primary
E-005 | Facebook crawler 403 is upstream of WordPress | Inference from evidence | HIGH CONFIDENCE | Crawler matrix + Wordfence absence + cPanel ModSecurity enabled | 2026-08-14 | Hosting operator | After rule lookup | Exact managed-rule ID not visible
A-001 | Organic leads may reach 12/month | Assumption | UNVALIDATED | Budget model base case | 2026-08-14 | Brokerage owner | After 30 days | Do not present as forecasted fact
D-001 | Form 7 consent wording | Owner decision | PENDING | OWNER_ACTIONS_REMAINING.md | 2026-08-14 | Brokerage owner/BIC | Before Form 7 activation | No Constant Contact activation before approval