## Executive Summary
Test Lead Register
Production test-governance register. No synthetic record is a live prospect.
Generated | 2026-08-14 17:31 ET
Data classification | Operational metadata only - no secrets, private BCC, or live customer PII

## Production Tests
Production Tests
Aggregate at audit: 6 tests, 0 live Neon prospects, 0 unsuppressed tests.
Test lead ID | Purpose | Date | Environment | Form | Suppression state | Notification state | Audit state | Reconciliation state | Retention decision
a1a7e899-9b2e-4ffe-968f-1e10728d60e8 | Initial public production QA/master | 2026-08-11 | production | Ask Magic Mike public seller | Suppressed | No outbound - invalid key stage | Audited | Reconciled | Retain as QA evidence
8609b5e2-da81-49b0-8db9-c113af6894a3 | Server-side QA marker verification | 2026-08-11 | production | Ask Magic Mike public seller | Suppressed | No outbound | Audited | Reconciled | Retain as QA evidence
59bba7cf-fe27-42c3-adb6-27b27727e5c7 | Verified sender end-to-end QA | 2026-08-11 | production | Ask Magic Mike /sell | Suppressed | One delivered internal alert | Audited | Reconciled | Retain as QA evidence
bbed9a2d-4619-4c18-9298-5167a9694f73 | Production cutover home-value QA | 2026-08-11 | production | Ask Magic Mike /value | Suppressed | One sent internal alert | Audited | Reconciled | Retain as QA evidence
70f63f35-2478-4738-b84c-bc1a89b8482c | WordPress Form 3 bridge acceptance | 2026-08-14 | production | Gravity Form 3 | Suppressed | One delivered internal alert | Audited | Reconciled | Retain as QA evidence
a7b1cf10-e546-48c4-85b1-2dee424ab156 | Pre-fix idempotency replay | 2026-08-14 | production | Gravity Form 3 replay | Suppressed after guarded transaction | None | Suppression audit added | Reconciled | Retain as incident evidence

## Automated Checks
Automated Checks
Required assertions for each release and daily reconciliation.
Check | Expected | Current result | Evidence
Unsuppressed tests | 0 | 0 | Neon aggregate query
Live lead marked test | 0 | Requires first-live-lead reconciliation | FIRST_LIVE_LEAD_RESPONSE_RUNBOOK.md
Tests in executive KPIs | 0 | 0 | Scoreboard COUNTIFS excludes Test?=Yes
Test consumer messages | 0 | 0 | Lead alert service suppression
Production tests with real customer data | 0 | 0 | QA evidence review