## Executive Summary
Evidence and Assumption Register
Separates verified production facts from hypotheses and owner decisions.
Generated | 2026-08-15 13:19 ET
Data classification | Operational metadata only - no secrets, private BCC, or live customer PII

## Evidence Register
Evidence Register
Do not convert assumptions into claims.
ID | Statement | Classification | Status | Source | Verified date | Owner | Next review | Notes
E-001 | AskMagicMike.com serves the canonical app | Evidence | VERIFIED | Vercel deployment dpl_3ogimm1EhHCaPkEfXLAeojrm2H8Z | 2026-08-15 | System owner | After next deploy | Production commit e754456cecaf6538df25bb4bf5eebe57ebf6eacb; apex redirects to www
E-002 | Form 3 creates one canonical lead and one internal alert | Evidence | VERIFIED | docs/FORM3_PRODUCTION_RECONCILIATION.md | 2026-08-14 | System owner | Daily | Replay idempotent
E-003 | Neon contains six suppressed QA leads and zero genuine live prospects at audit | Evidence | POINT-IN-TIME | Neon production aggregate at 2026-08-15T16:35:23Z | 2026-08-15 | System owner | Daily | Zero QA in Active/New; zero unsuppressed QA
E-004 | Web Push has zero active devices | Evidence | VERIFIED | Neon staff_push_subscriptions aggregate | 2026-08-15 | System owner | After physical enrollment | Email remains primary
E-005 | Meta crawler receives 403 on two Our Town URLs only | Evidence | OPEN HOSTING ACTION | 40/42 crawler matrix; other crawlers and Ask Magic Mike URLs pass | 2026-08-15 | Hosting operator | After narrowly scoped host review | Do not weaken the firewall broadly
E-006 | First-live and SLA monitors are scheduled | Evidence | VERIFIED | Vercel cron logs and vercel.json | 2026-08-15 | System owner | Daily | First-live every 2 minutes; SLA hourly
A-001 | Organic leads may reach 12/month | Assumption | UNVALIDATED | Budget model base case | 2026-08-14 | Brokerage owner | After 30 days | Do not present as forecasted fact
D-001 | Form 7 consent wording | Owner decision | PENDING | OWNER_ACTIONS_REMAINING.md | 2026-08-14 | Brokerage owner/BIC | Before Form 7 activation | No Constant Contact activation before approval