## Executive Summary
WordPress Form Activation Matrix
Controlled form-by-form canonical activation register. Form 3 is the verified baseline.
Generated | 2026-08-15 13:19 ET
Data classification | Operational metadata only - no secrets, private BCC, or live customer PII
Active canonical forms
Shadow forms
Blocked/deferred forms
Live prospects in Neon | 0
Unsuppressed tests | 0

## Form Inventory
Form Inventory
Source: authenticated Gravity Forms and rendered public sitemap, 2026-08-14.
Form ID | Form name | Public URL | Lead type | Current status | Bridge version | Allowlisted? | Local Gravity entry? | Canonical endpoint | Current notifications | Duplicate-notification candidate | Consent fields | Attribution fields | Canonical field mapping | Routing rule | Assigned owner | QA status | Activation date | Rollback package | Notes
1 | Contact Us | https://www.ourtownproperties.com/contact-us/ | general_question | SHADOW - READY FOR QA | 1.1.0 | No | Yes | POST /api/leads | Admin Notification (active) | Yes after canonical QA | No native Consent field; absent permissions default false | UTM/click IDs via bridge context | name 1; email 2; phone 6; subject 3; message 4 | Route to Mike | Mike/admin review | Not run |  | Per-form 1.1.0 config + GF export | Use denied consent defaults until approved wording
2 | Cash Offer Form | No rendered sitemap placement found | seller_cash_offer | SHADOW - MAPPING REQUIRED | 1.1.0 | No | Yes | POST /api/leads | Admin Notification (active) | Yes after canonical QA | No native Consent field | UTM/click IDs via bridge context | name 1; phone 7; email 2; address 6 | Route to Mike | Mike | Not run |  | Per-form 1.1.0 config + GF export | Brokerage review of seller-options copy required
3 | Home Value Form | https://www.ourtownproperties.com/how-much-is-your-home-worth/ | home_value | ACTIVE - CANONICAL | 1.1.0 | Yes | Yes | POST /api/leads | Admin Notification (inactive duplicate) | Corrected | Denied call/email/SMS stored for QA | Verified first/last touch and UTMs | address 6; name 1; email 2; phone 7 | Route to Mike | Mike | PASS | 2026-08-14 | wordpress-canonical-bridge-1.0.0-rollback.zip | Entry 1549; one canonical lead; one alert; replay idempotent
4 | Join Our Team Form | https://www.ourtownproperties.com/join-our-team/ | recruiting | NOT A LEAD FORM | 1.1.0 | No | Yes | Not activated | Admin Notification (active) | No | No native Consent field | UTM context available | name 1; phone 7; email 2; license 8; address 6 | Recruiting/admin only | Unverified | Not applicable |  | GF export | Keep outside consumer routing
5 | Rental Property Search | No rendered sitemap placement found | renter | SHADOW - MAPPING REQUIRED | 1.1.0 | No | Yes | POST /api/leads | Admin Notification (active) | Yes after canonical QA | No native Consent field | UTM/click IDs via bridge context | name 1; phone 7; email 2; address 6; area 8 | Mike or admin review | Unverified | Not run |  | Per-form 1.1.0 config + GF export | Confirm public placement and recipient
6 | Short Term Home Rentals form | https://www.ourtownproperties.com/short-term-home-rentals/ | renter | SHADOW - READY FOR QA | 1.1.0 | No | Yes | POST /api/leads | Admin Notification (active) | Yes after canonical QA | No native Consent field | UTM/click IDs via bridge context | name 1; phone 7; email 2; details 8 | Mike/admin review | Mike/admin review | Not run |  | Per-form 1.1.0 config + GF export | Controlled QA after denied-consent mapping
7 | Never miss a property! | Global/sitewide placement | buyer_property_alert | DEFERRED - LEGAL REVIEW | 1.1.0 | No | Yes | POST /api/leads after consent fix | Admin Notification (active) | Yes after canonical QA | No explicit marketing Consent field | Page and campaign context required | name 1; phone 7; email 2; message 8 | Mike until approved mapping | Mike/admin review | Blocked |  | Per-form 1.1.0 config + GF export | Possible genuine entry 1550 preserved; do not use as QA
Summary

## Activation Gates
Activation Gates
Use PASS, FAIL, N/A, or PENDING. Eligibility is formula driven.
Form ID | Form name | Backup complete | Field mapping complete | Consent mapping complete | Attribution mapping complete | Routing tested | Signature tested | Replay tested | Local entry verified | Neon record verified | Canonical ID verified | Internal alert verified | Hidden BCC verified | Consumer message suppressed | SMS suppressed | Duplicate notification corrected | Rollback tested | Production health passed | Completion % | Activation eligibility | Remaining blockers
1 | Contact Us | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING
2 | Cash Offer Form | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING
3 | Home Value Form | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
4 | Join Our Team Form | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5 | Rental Property Search | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING
6 | Short Term Home Rentals form | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING
7 | Never miss a property! | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING | PENDING

## QA Evidence
QA Evidence
No private BCC values or secrets.
QA test ID | Form ID | Date | Gravity entry ID | Canonical lead ID | Resend provider ID | Notification count | Replay result | Suppression result | Test-record status | Cleanup/reconciliation status | Evidence path | Pass or fail
FORM3-QA-20260814 | 3 | 2026-08-14 | 1549 | 70f63f35-2478-4738-b84c-bc1a89b8482c | bf31a582-e4a3-45cb-a7f1-5cb89121626f | 1 | Same lead; no new message | PASS | is_test=true | Suppressed and retained | docs/FORM3_PRODUCTION_RECONCILIATION.md | PASS

## Rollback Register
Rollback Register
Never delete Gravity entries during rollback.
Form | Previous state | Current state | Notification state | Bridge state | Backup package | Rollback steps | Rollback test date | Owner | Status
Form 1 - Contact Us | Native notification active; not allowlisted | Unchanged/shadow | Admin Notification (active) | Not allowlisted | Per-form 1.1.0 config + GF export | Disable per-form forwarding; restore only proven duplicate notification; preserve entries |  | Mike/admin review | AVAILABLE
Form 2 - Cash Offer Form | Native notification active; not allowlisted | Unchanged/shadow | Admin Notification (active) | Not allowlisted | Per-form 1.1.0 config + GF export | Disable per-form forwarding; restore only proven duplicate notification; preserve entries |  | Mike | AVAILABLE
Form 3 - Home Value Form | Native notification active; bridge shadow | Canonical active | Admin Notification (inactive duplicate) | Allowlisted | wordpress-canonical-bridge-1.0.0-rollback.zip | Disable per-form forwarding; restore only proven duplicate notification; preserve entries | 2026-08-14 | Mike | PASS
Form 4 - Join Our Team Form | Native notification active; not allowlisted | Unchanged/shadow | Admin Notification (active) | Not allowlisted | GF export | Disable per-form forwarding; restore only proven duplicate notification; preserve entries |  | Unverified | AVAILABLE
Form 5 - Rental Property Search | Native notification active; not allowlisted | Unchanged/shadow | Admin Notification (active) | Not allowlisted | Per-form 1.1.0 config + GF export | Disable per-form forwarding; restore only proven duplicate notification; preserve entries |  | Unverified | AVAILABLE
Form 6 - Short Term Home Rentals form | Native notification active; not allowlisted | Unchanged/shadow | Admin Notification (active) | Not allowlisted | Per-form 1.1.0 config + GF export | Disable per-form forwarding; restore only proven duplicate notification; preserve entries |  | Mike/admin review | AVAILABLE
Form 7 - Never miss a property! | Native notification active; not allowlisted | Unchanged/shadow | Admin Notification (active) | Not allowlisted | Per-form 1.1.0 config + GF export | Disable per-form forwarding; restore only proven duplicate notification; preserve entries |  | Mike/admin review | AVAILABLE